## Ashley Kelley
Week 4 Individual Journal
Date | Task | Summary
2021-11-17 | WBS in Microsoft Project | Created a WBS to ensure proper scheduling of all tasks related to the project. I assigned jobs to different team members. I set all the dates and estimated times for each individual task.
2021-11-20 | Software Requirements Specification | Reviewed and corrected necessary items in the software requirements section and changed things as discussed within the group.
Week 5 Individual Journal
Date | Task | Summary
2021-11-25 | WBS in Microsoft Project | Updated WBS for current week.
11/24/2021- 11/25/2021 | Risk Assessment | Completed the risk assessment. This is including all risks, possible outcomes, possible hazards, risk ownership, risk scores and response strategies.
11/27/2021- 11/28/2021 | Software Requirements Specification | Completed use case specifications and added all necessary components.
Week 6 Individual Journal
Date | Task | Summary
2021-11-30 | Update WBS in Microsoft Project | Updated WBS for current week and add all test cases to the schedule.
12/1/2021-12/3/2021 | 2.12-2.13 and Test Case 1 | Completed risk and contingencies, and test case 1. Researched and helped other teammates.
2021-12-05 | Journal entries and combining the project. | Added all parts of the project together.
Week 8 Individual Journal
Date | Task | Summary
2021-12-06 | Powerpoint and WBS | Updated WBS for current week and add all test cases to the schedule. Put powerpoint presentation together.
2021-12-07 | Project summary evaluation | Completed slide for project.
2021-12-16 | Journal entries and combining the project. | Combining and submitting assignment

## Kimberly Hernandez
Week 4 Individual Journal
Date | Task | Summary
2021-11-17 | Software Requirements Specifiations | Started on template from section 1.1 Introduction to 1.2.3 User Classes and Characteristics. Section 1.2.2 Product Functions was revised based on group discussion. Some research was conducted for 1.2.3 User Classes and Characteristics section to confirm product users.
2021-11-18 | Software Requirements Specifiations | Continued template on section 1.2.4 to 1.3.4 Communication interfaces. Research was done to confirm operating systems and versions for the game to run on. Research also included finding typical server expectations.
Week 5 Individual Journal
Date | Task | Summary
2021-11-24 | Sequence Diagram | Worked on the sequence diagram based on the Hunter part of the Use Case Diagram. Continued the sequence diagram based on the Prey Use Case Diagram. Research was done to verify activation for each object.
2021-11-27 | State Machine Diagram | Worked on state machine diagram based on weapon class. Research was done to verify state machine diagram components.
2021-11-28 | Project Level Summary Evalutaion-Analysis Design | Worked on and completed the project level summary. Research was done on common game development risks.
Week 6 Individual Journal
Date | Task | Summary
2021-11-30 | Test Case #2, Environmental Needs, Features to be Tested | Worked on section 3.2 Test Case #2 character limit/avilability and part of section 2.9 Environmental Needs. Reviewed SRS document from week 4 to include that details for enviormental needs also include system requirements listed in SRS document. Based on discussion the SRS document was also used to for applicable test cases for section 3.2 Test Cases in which 2 were applied from original features and 2 were created. Also completed section 2.4 Features to be tested.
2021-12-01 | Environmental Needs, Features not to be Tested, Test Items, Test Plan Identifier | Finished section 2.9 Environmental Needs after researching this section. Researched for approaches on game development testing environments and on bug reporting tools as well as reporting documents. Also completed sections 2.1 Test Plan Identifier, 2.3 Test Items, and 2.5 Features not to be Tested.
Week 8 Individual Journal
Date | Task | Summary
2021-12-06 | MS Word Template | Transferred all project information to the template and completed all sections that needed to be completed for the Project summary.
2021-12-07 | Project Summary Slide | Completed summary slide and submitted for review and adding to presentation.

## Kevin Overton
Week 4 Individual Journal
Date | Task | Summary
2021-11-17 | Use Case Diagram 1 | Created a use case diagram detailing the functions a player can use during the game.
2021-11-18 | Use Case Diagram 2 | Expanded the use case diagram with five new requirements: lobby, friends, chat, coins, animal skills. Actor "Server" added to show connectivity and other non-player functions necessary to support player functions.
Week 5 Individual Journal
Date | Task | Summary
2021-11-28 | Class Diagram | Created a class diagram showing some of the classes needed to create a functional game.
Week 6 Individual Journal
Date | Task | Summary
2021-12-05 | Test Case #4 | Created a test case for testing the functionality of all in-game weapons and items useable by the hunter player.
2021-12-05 | Test Plan sections 2.6, 2.7, 2.8, 2.10, 2.11 | Detailed the test plan sections for Approach, Items Pass/Fail Criteria, Test Deliverables, Responsibilties, Staffing and Training Needs.
Week 8 Individual Journal
Date | Task | Summary
2021-12-10 | Course evaluation slide | Wrote my course evaluation slide and submitted it to group to add to project and completed other assigned parts of the project.

## Tiffany McArthur
Week 4 Individual Journal
Date | Task | Summary
2021-11-20 | Software Requirements Specifiations | Started template on 1.4 System Features finishing on 1.6.5 Business rules. Revised information according to group discussion.
Week 5 Individual Journal
Date | Task | Summary
2021-11-26 | Researched different risks | I reviewed different risks that could affect our project.
2021-11-28 | Project Level Summary Evaluation | Analyzed overview of project and determined what we could do better. Also interpreted how we all understand the risks that could affect the project. Listed a few more risks that could affect the project.
Week 6 Individual Journal
Date | Task | Summary
2021-11-30 | Review | Reviewed assignment requirments.
2021-12-03 | Test Case 3 | Completed test case for storage capability and system requirements
2021-12-05 | 1.1 and 2.2 | Completed testing evaluation and test plan introduction
Week 8 Individual Journal
Date | Task | Summary
2021-12-10 | Evaluation slide | Created the slide to add to the group project and completed all other assigned parts of the project.