## Sheet1
Qualitative Risk Analysis
ID | Category | Risk Name | Risk Description | Risk Owner | Reason/Cause | Effect | Probability | Impact/Cost | Impact/Time | Impact/Quality | Risk Score | Risk Response Strategy | Cost
1 | Technical | Design not approved on time | Design approvals delayed or not submitted on time | Designer | Availability | Delay of development | 3 | 5 | 5 | 3 | 3 | Schedule design review meetings one week prior to deadline. | 10000
2 | Project Management | Going over budget | Budget not enough to cover expenses | Finance | Availability | Not enough money to move forward | 3 | 5 | 2 | 3 | 3 | Make a plan and plan any overages that could occur before starting the project | 10,000-50,000
3 | Organizational | Customer data integrity | Wrong or altered data entered | Specialist | Errors | Data integrity | 3 | 3 | 5 | 5 | 3 | Validate data on data sample | 5000
4 | Technical | Network issues | Issues with the network during the project and while implementing the new game | Network services | Network | Development delay | 2 | 2 | 3 | 5 | 2 | Make sure that there is a proper connection before implementing | 3000
5 | Technical | Not reaching deadlines | Project parts not completed on time and submitted for review | Project manager | Availability | Development delay | 1 | 3 | 3 | 2 | 0.6 | Check that everything is on schedule and check in with team members to ensure that everything is on schedule weekly. | 5000
6 | Technical | Implemention issues | Implementation doesn’t go as planned | Developer 1 | Development | Development delay | 3 | 2 | 2 | 3 | 1.8 | Check for errors and correct anything that may be off | 3000
7 | Technical | Program bugs | The program was moved forward with bugs that were not detected before moving to the next stage of programming | Developer 2 | Development | Development issues | 2 | 4 | 5 | 5 | 2 | Make sure that there is no bugs seen or unseen before moving forward with the next stage of develoment | 7000
8 | Organizational | Potential hires lose interest | Potential hires or selected team members losing interest in the project and having to select new people | Management | Hiring | Could allow for better options | 1 | 1 | 2 | 1 | 0.4 | Ensure engagement ahead of time, draw up contracts or have backups in case of a fall through. This could lead to better team options because someone that is not motivated in the project could lead to team failure rather than success | 1000
9 | Organizational | Lack of communication | Not enough communication between team members | Communitcations | Communications | Errors in project | 2 | 1 | 2 | 4 | 1.6 | Setup scheduled meetings and communications between team members to ensure proper communication | 1000
10 | External | Security issues | Problems with security during the launch | Cyber security 1 | Security | Development delay | 2 | 2 | 4 | 4 | 1.6 | Ensure that there are proper security protocols setup before launch | 3000
11 | External | Hackers | Hackers getting through unpatched holes in the program | Cyber security 2 | Security | Compromised data | 2 | 5 | 5 | 5 | 2 | Find and test any holes in the software and patch them before hackers can get through them | 10000
12 | Technical | Internet connection | The internet connection is not fast enough for the development and launch of program | IT 2 | Network | Development delay | 1 | 2 | 2 | 5 | 1 | Test internet speed and connection before launch | 3000
13 | Organizational | Network capacity | Not enough network capacity to handle the game and causes a failure during game | Network services | Network | Development delay | 1 | 1 | 4 | 5 | 1 | Conduct network assessment and troubleshoot prior to migration | 1000
14 | Organizational | Data errors | Field mapping errors | Architect | Errors | Errors in project | 2 | 2 | 2 | 4 | 1.6 | Test mapping on data sample | 3000
15 | Project Management | Going far below budget | Miscalculation leads to a budget surplus | Accounting | Miscalculation | Company saved money | 2 | 1 | 1 | 1 | 0.4 | Put remaining budget back to use funds elsewhere | 1000
16 | Organizational | Risk in development | Taking a risk and creating a new product can be challenging but can gain new business | Development team | Abundance of interest | New business gained | 3 | 1 | 1 | 1 | 0.6 | Allocate resources to create availability to new customers | 1000
16 | Technical | Technology | Creating a product to be more efficient and create a great and fun game | IT | Greater efficiency | Faster service, more sales | 3 | 1 | 3 | 3 | 1.8 | Enjoy the benefits | 1000
17 | Technical | Advancing in technology | Too much desire for our personnel and technology to handle | IT | Better system | Less labor costs | 3 | 1 | 3 | 3 | 1.8 | Increase server and gaming software and hardware to acommodate new players. | 1000
The risk score is calculated from the probability multiply by the highest risk score (1–5) divided by 5 to give an average risk score between 1 and 5.
Score between 4 and 5
Score between 2 and 3.99
Score between 0 and 1.99